## SIFCA Biodiversity Action Plan
SIFCA GROUP'S ACTION PLAN 2021-2024 FOR BIODIVERSITY CONSERVATION AND ZERO DEFORESTION
N° | Actions / Requirement | GPSRN Policy Component | BONSUCRO Policy Component | RSPO Policy Component | Current or future projects or initiatives | Indicator | Results / Deliverables | Stearing | Implementation period | [5 empty] | Deadline | Status
[9 empty] | Execution | An 1 | An 2 | An 3 | An 4 | An 5 |  | PALMCI | SUCRIVOIRE | SAPH | GREL | CRC | MOPP | RENL | SD GROUP's Comment | Need in terms of budget
ORIENTATION 1 : ASSESS THE POTENTIAL OF OUR BIODIVERSITY
ACTION 1: Organize the biodiversity management framework | Organiser un comité de cogestion des écosytèmes biologiques
1.1.1 | Re-organize the biodiversity committee by including community representatives, through the Stakeholder Engagement Framework (SEF) members |  |  |  | N.A | Local organization is part of the biodiversity committee | List of biodiversity committee members available | SD/IB | Site | X |  |  |  |  | 2021-09-30 | En cours | En cours | En cours | not started | not started | non entamé | not started
1.1.2 | Define biodiversity management performance indicators on site |  |  |  | N.A | performance indicator support is available | Site Performance Indicators Document | SD/SD site/Biodiversity Engenieer (BE) | SD/SD site/BE | X |  |  |  |  | 2021-07-12 | En cours | En cours | En cours | not started | not started | non entamé | not started
1.1.3 | Define SIFCA performance indicators in zero deforestation policy |  |  |  | N.A | performance criteria support is available | SIFCA group performance indicators document | SD/BE | SD/BE | X |  |  |  |  | 2021-07-12 | En cours | En cours | En cours | not started | not started | non entamé | not started
ACTION 2 : Make an inventory of all the ecological zones on sites
1.2.1 | Develop a toolkit for identifying biodiversity areas |  |  |  | N.A | Identification toolkit and biodiversity criteria is available | Toolkit for identification and biodiversity criteria is available | SD/BE | SD/BE | X |  |  |  |  | 2021-07-28
1.2.2 | Make an inventory of potential areas of biodiversity and peat | Criteria 2.1.1 Criteria 2.7 | Criteria 4.1 | Criteria 7.7 | N.A | 1 exhaustive list of biodiversity zones by site | GPS coordinates of available biodiversity areas | SD/BE | Site | X | X | X | X | X | 15/06 | En cours | En cours | En cours | not started | En cours | En cours | En cours
1.2.3 | Evaluate the number of hectares planted, the survival rate and the dendrometric characteristics of the plants |  |  |  | N.A | Assessment report / Biodiversity management plan | Number of hectares planted / Plant survival rate / Dendrometric characteristics | SD/BE | National Firm | X |  |  |  |  | 2021-10-20 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.2.4 | Evaluate the area / biodiversity area to be planted |  |  |  | N.A | Assessment report | Number of hectares to be planted / Number of plants to produce or buy | SD/BE | National Firm | X |  |  |  |  | 2021-10-20 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.2.5 | Develop the biodiversity zones mapping on sites |  |  |  | N.A | Map per biodiversity zone is available | Mapping of areas to be protected available | SD/ Estate Department (ED) | cartography service | X | X | X | X | X | 15/07 | Non entamé | ok | ok | ok | not started | non entamé | not started
1.2.6 | Design a restoration and / or protection program for biodiversity and peatland areas | Criteria 2.2 | Criteria 4.1 | Criteria 7.7 Criteria 7.12 | N.A | restoration and protection program for biodiversity areas is available | Restoration and protection program for biodiversity areas available | SD/BE/Foundation | BE/Site/Foundation | X | X | X |  |  | 2021-03-26 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.2.7 | Make an inventory of fauna and flora in the preserved areas |  |  |  | N.A | fauna and flora inventory report available | Inventory carried out | SD/ ED/BE | International firm / National firm / SODEFOR / Site |  | X | X | X | X | 15/08 | Non entamé | En cours | Non entamé | not started | not started | Non entamé | not started
ACTION 3 : Build the capacity of stakeholders in the conservation of protected areas
1.3.1 | Train the biodiversity committee members on the identification of areas of value to be protected (Industrial Plantation and in surrounding communities) |  |  |  | N.A | training report available | Trainings carried out and training report available; Trained actors | SD/BE | Consultant | X | X |  |  |  | 14/02 | A renouveler | A renouveler | A renouveler | not started | not started | Non entamé | not started
1.3.2 | Build headoffice and on site staff capacity on the protection of biodiversity for the sustainability of the Group's activities |  |  |  | N.A | training report available | Trainings carried out and training report available; Trained actors | SD/BE | SD/BE | X | X | X |  |  | 15/12 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.3.3 | Build the capacity of biodiversity committees on the toolkit to identifying biodiversity |  |  |  | N.A | training report available | Training carried out and training report available; | SD/BE | SD/BE |  | X | X | X |  | 16/03 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.3.4 | Train the biodiversity committee members on conservation techniques for protected areas |  |  |  | N.A | training report available | Training carried out and training report available; Trained actors | SD/BE | Consultant |  | X | X | X | X | 20/04 | A renouveler | A renouveler | A renouveler | not started | not started | Non entamé | not started
1.3.5 | Build the capacity of eco-guard teams on techniques for monitoring and protecting biodiversity |  |  |  | N.A | training report available | Training carried out and training report available; | SD/BE | Consultant |  | X | X | X | X | 30/05 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
1.3.6 | Train a staff per sector on HCV / HCS assessment skills according to PROFOREST requirement |  |  |  | N.A | 3 training certificate | Training carried out | BE/PROFOREST | PROFOREST |  | X | X | X | X | 2025-12-15 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
ORIENTATION 2 : CONSERVE-PRESERVE
ACTION 1 : Implement the Biodivestity Conservation Plan
2.1.1 | Evaluate the number of sign boards to be installed |  |  |  | N.A | 1 assessment report of the number available sign boards | Evaluation report | SD/BE | SITE/BE | X |  |  |  |  | 2021-10-30
2.1.2 | Design the signs board model and physically mark all the areas to be protected |  |  |  | N.A | sign board installation report | sign board posting and / or signage | SD/COM/BE | BE/COM/Site | X |  |  |  |  | 2021-12-30 | Non entamé | En cours | En cours | ok | not started | Non entamé | not started
2.1.3 | Build the capacity of the biodiversity committee on techniques for restoring biodiversity areas |  |  |  | N.A | training report available | Trainings carried out and training report available; | SD/BE | Site/BE |  | X |  |  |  | 2022-02-15
2.1.4 | Implement the restoration and protection program of biodiversity zones | Criteria 2.2 | Criteria 4.1 |  | Projet de reboisement SUCRIVOIRE-SODEFOR; projet agroforesterie SIFCA - AMISTAD; Projet d'écocitoyenneté SIFCA IVOIRE DD | Progress report on the restoration plan | Reduction of adverse influences and enhancement of the biological characteristics of biodiversity areas | SD | Site/NGO/Firm |  | X | X | X |  | 2024-08-15 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
ACTION 2 : Develop mechanisms for the participation of local communities in the sustainable management of protected areas and identified sensitive areas
2.2.1 | Develop mechanisms for the participation of local communities in the sustainable management of protected areas and identified sensitive areas | Criteria 2.2 |  |  | Projet 01 école 05 ha; AMISTAD; Projet de reboisement SUCRIVOIRE-SODEFOR | Number of agreements signed between the SIFCA group and a development partner Number of project documents available | Benchmark carried out or memorandum of understanding signed; Project document | SD Site/ SD SIFCA | SD site/ SD SIFCA | X | X | X |  |  | 2023-08-10 | En cours | En cours | En cours | not started | not started | Non entamé | not started
ORIENTATION 3: MANAGE, EVALUATE AND CORRECT
ACTION 1 : To manage, monitor and evaluate the process of carrying out the activities of the Strategy and the Action Plan as a way to ensure better conservation and sustainable use of the resources of our sites' biological diversity
3.1.1 | Disseminate (sensitize) widely and at all levels and especially among neighboring communities, opinion makers, teachers, knowledge and information on the importance of the conservation of biological diversity and the fight against wildfires. | Criteria 2.3 |  | Criteria 7.11 | Projet 01 école 05 ha; AMISTAD; Projet de reboisement SUCRIVOIRE-SODEFOR | Number of people sensitized Number of hectares planted or reforested | Increase awareness raising of stakeholders / Awareness reports | Site Biodiversity Commission | Site Biodiversity Commission | X | X | X | X | X | 20/08 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.2 | Make an inventory of biodiversity and peatland areas before any new clearing | Criteria 2.1.1 Criteria 2.7 | Criteria 4.1 | Criteria 7.12 Criteria 7.7 |  | Number of Land Use Map / Land Use Change Project | Risk analysis report | SD/IB | BE | X | X | X | X | X | 15/10 | Non entamé | Non entamé | En cours | not started | En cours | Non entamé | not started
3.1.3 | Follow up on actions related to HVC / HCS studies | Critère 2.1.1 | Criteria 4.1 | Criteria 7.12 | N.A | on site HVC / HCS zones Maps | HVC-HCS study reports | SD/IB | Firm | X | X | X | X | X | 15/10 | Non entamé | Non entamé | En cours | not started | En cours | Non entamé | not started
3.1.4 | Carry out satellite monitoring of biodiversity zones in Technical Assistance with donors |  |  |  | SATELLIGENCE BV | Visit frequency to the monitoring platform Monitoring report | Satellite image available | SD/IB | BE | X | X | X | X | X | N.A | En cours | En cours | En cours | not started | En cours | Non entamé | not started
3.1.5 | Define an early warning protocol and a monitoring system for biodiversity zones (action plan) |  |  |  | N.A | Number of visits Number of alerts launched | Early warning protocol Map of the biodiversity zones Quarterly visit report | Site Biodiversity Commission | Site Biodiversity Commission | X | X | X |  |  | 15/11 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.6 | Identify deforestation and bushfire hotspots | Criteria 2.3 | Criteria 4.1 | Criteria 7.11 | SATELLIGENCE BV | Report of the physical status of biodiversity zones | Satellite image available; Action plan available | SD/BE | BE | X | X | X | X | X | 30/11 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.7 | Implement an action plan to raise public awareness and strengthen protection targeted around areas with deforestation and bush fire hotspots | Criteria 2.3 | Criteria 4.1 | Criteria 7.11 | SATELLIGENCE BV | Number of action plans to raise public awareness and strengthen protection | Action plan implementation report | SD/BE | Site | X | X | X | X | X | 30/11 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.8 | Evaluate the level of implementation and the impact of local farms in protected forests, national parks and identified HVC-HCS areas | Criteria 2.1.1 Criteria 2.1.2 Criteria 2.7 | Criteria 4.1 | Criteria 7.12 |  | Land use map | Risk analysis report | BE/SD Site | BE/SD Site/biodiversity Commission | X | X | X | X |  | 20/12 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.9 | Evaluate the level of sites' compliance with respect to the Group's biodiversity rules | Criteria 2.1.1 Criteria 2.1.2 Criteria 2.7 | Criteria 4.1 | Criteria 7.7 Criteria 7.12 | N.A | Appraisal sheet Audit assignment per site | Compliance report | BE/SD Site | BE/SD Site/biodiversity Commission | X | X | X | X | X | 20/09 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.10 | Evaluate the Group's level of compliance with its zero deforestation policy | Criteria 2.1.1 Criteria 2.1.2 Criteria 2.7 | Criteria 4.1 | Criteria 7.7 | N.A | Appraisal sheet Audit assignment per subsidiary | Compliance report | SD | SD/SD site | X | X | X | X | X | 02/10 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.11 | Identify and assess the greenhouse gas emissions of SIFCA group's activities |  | Criteria 3.2 | Criteria 7.10 |  | GHG report available | GHG emission report reports | SD | Firm |  | X | X | X |  | 2024-10-05 | Non entamé | Non entamé | En cours | not started | not started | Non entamé | not started
3.1.12 | Develop and implement a plan to reduce greenhouse gas emissions for the SIFCA group (climate strategy) |  | Criteria 3.2 | Criteria 7.10 |  | Continuous GHG Reduction Plan | GHG reduction activity report | SD | Firm/BE |  |  | X | X | X | 2025-10-06 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
3.1.13 | Carry out a stored SIFCA group's annual carbon footprint |  | Criteria 3.2 | Criteria 7.10 | N.A | Carbon footprint available | Carbon footprint report | SD | Firm | X | X | X | X | X | 02/11
3.1.14 | Develop an annual report template and implement (Site / SIFCA) |  |  |  | N.A | Report template available | Report template available | SD/BE | BE | X |  |  |  |  | 2021-11-05
3.1.15 | Prepare annual reports on the progress made in order to update the conservation action plan |  |  |  | N.A | 1 annual report available | Annual reports prepared; Known gaps; Updated action plan | SD/BE | SD/BE | X | X | X | X | X | 02/12 | Non entamé | Non entamé | Non entamé | not started | not started | Non entamé | not started
ORIENTATION 4 : SPREADING
ACTION 1 : Develop private to private partnership with our clients for the creation, conservation, protection and management of biodiversity
4.1.1 | Identify partners (NGOs, Academics, etc.) or clients on biodiversity or forest conservation or restoration projects | Criteria 2.1.1 Criteria 2.1.2 Criteria 2.2 Critère 2.3 | Criteria 4.1 | Criteria 7.12 | SATELLIGENCE BV; AMISTAD; Convention MINEF, CONVENTION espèces marines, projets de convention OIPR, Convention SODEFOR | Number of agreements signed Number of Co-projects developed | Project documents available | SD/SD site | SD/SD site | X | X | X | X | X | 26/10 | Non entamé | En cours | Non entamé | Non entamé | Non entamé | Non entamé | not started
4.1.2 | Identify critical areas / habitats for the survival of endangered species and plants and contribute to their preservation / restoration | Criteria 2.4 | Criteria 4.1 | Criteria 7.12 | SATELLIGENCE BV; AMISTAD; Convention MINEF, CONVENTION espèces marines, projets de convention OIPR, Convention SODEFOR | Protected habitat area Number of protected species | Project documents available Project assessment reports available | SD/BE/Foundation | SD/BE/Foundation |  | X | X | X | X | 26/11 | En cours | En cours | Non entamé | Non entamé | Non entamé | Non entamé | not started
Note on C23: HP: Je voudrais prendre connaissance des modules abordés afin d'évaluer le besoin d'y intégrer de nouveaux
Note on C39: AGOH N'Guessan Jean-Luc: Déplacer depuis l'orientation 1
Note on G42: NOUFE Sie: Ce n'est pas eux de proposer des actions!!!!